## Estimation
Component | Requirements ID | Item | Description | Estimation | [14 empty] | Sprint | Delivery Plan
|  |  |  | Planning/ Req analysis | POC | UI Design | Backend | Integration | Object Design | UT | Review | Development Total | Number of Test Cases | Test Case Design | Test Case Execution | IT total | Fixing and verification | Total
Medication | PC0001 | New Medications | Form to create medications | 1 | 10 | 5 | 5 | 5 | 0 | 2 | 1 | 29 | 5 | 2 | 0.5 | 2.5 | 0 | 31.5 | Sprint 1
| PC0002 | View Medications | Panel to view the medications | 1 | 20 | 10 | 10 | 10 | 0 | 2 | 1 | 54 | 5 | 2 | 0.5 | 2.5 | 0 | 56.5 | Sprint 1
Mood | PC0003 | New Mood Insert | Form to insert mood information | 1 | 2 | 2 | 2 | 2 | 0 | 2 | 1 | 12 | 5 | 2 | 0.5 | 2.5 | 0 | 14.5 | Sprint 2
| PC0004 | Result from the Mood Poll | See results from the queries. | 1 | 20 | 10 | 10 | 10 | 0 | 2 | 1 | 54 | 5 | 2 | 0.5 | 2.5 | 0 | 56.5 | Sprint 2
| PC0005 | View All Mood Data's | Panel to view the Mood Data | 1 | 5 | 5 | 5 | 5 | 0 | 2 | 1 | 24 | 5 | 2 | 0.5 | 2.5 | 0 | 26.5 | Sprint 2
Symptoms | PC0006 | New Symptoms Insert | Form to insert Symptoms information | 1 | 2 | 2 | 2 | 2 | 0 | 2 | 1 | 12 | 5 | 2 | 0.5 | 2.5 | 0 | 14.5 | Sprint 3
| PC0007 | Result from the Symptoms Poll | See results from the queries. | 1 | 2 | 2 | 2 | 2 | 0 | 2 | 1 | 12 | 5 | 2 | 0.5 | 2.5 | 0 | 14.5 | Sprint 3
| PC0008 | View All Symptoms Data's | Panel to view the Symptoms Data | 1 | 2 | 2 | 2 | 2 | 0 | 2 | 1 | 12 | 5 | 2 | 0.5 | 2.5 | 0 | 14.5 | Sprint 3
Report | PC0009 | Get Report | Download the patient's report | 4 | 20 | 4 | 10 | 4 | 0 | 2 | 1 | 45 | 5 | 2 | 0.5 | 2.5 | 0 | 47.5 | Sprint 4
[12 empty] | 105 |  |  | 0 | 0 |  | 117.5